|  |  |  |  |
| --- | --- | --- | --- |
| **Topic &**  **reference in BNDP** | **Parish Action Points (PAP)** | **Actions completed** | **Comments** |
| **ON HOLD or ACTION REMOVED** | | | |
| **PAP 7**  **Greenspace south off**  **Eastway** | The potential for public access and use for the green space south of Eastway will be pursued | Story Homes report that they will be keeping the land for the 20 year period.(2033)  As yet ownerships has not transferred to  Story Home from Homes England.  Public access is a principle the PC will support & pursue. | Dialogue established in 2019 no progress to date |
| **PAP 8 Village gateways** | Proposals to create gateway features to give a strong sense of arrival will be developed | Possibility of Roundabout sculpture/flower beds LCC contacted 23/02/19 no response to date, on hold due to restricted funds | Midas developments were interested in the roundabouts details passed to LCC no response to date |
| **Heritage Assets**  PAP 9A & B | Conservation area(s) & buildings within them to be discussed:  Church Hamlet & High Street | Conservation area discussed with residents and are not to be progressed |  |

|  |  |  |  |
| --- | --- | --- | --- |
| **Topic &**  **reference in BNDP** | **Parish Action Points (PAP)** | **Actions completed** | **Comments** |
| **POLICY** | | | |
| **Community Infrastructure Levey (CiL)** | The Parish Council (PC) will support with  **Community Grants** infrastructure projects in the Village that meet the criteria of the CiL | Application forms on the website updated  List of allocated funds on website  Allocation dependent on income received | CiL grants are available, **matched funding required 2024/25 limit 10K per application** |
| **Communication** | The Parish Council will make sure all methods of communication are used to enable as broad a number of people can access information The Parish Council will support new and existing businesses | Media: Website, Facebook, E-news every 4 months, Press releases  Compliance with GDPR monitored  Notice Boards X 3: open to community  Village Information sessions continue 3 times a year | Facebook & website Cllr Bell is the social media & the clerk is the web manager for the council.  Notice board on Eastway site managed by a resident |

|  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- |
| **Topic & reference in BNDP** | **Action points**  **Areas with limited progress since 2022 highlighted in red** | **Update on actions to date** | **Target** | **Planned expenditure 2021/22** | | |
| **Precept** | **Other** | **CiL** |
| **ONGOING** |  |  |  |  |  |  |
| **PAP 4 primary School** | “Proposals additional places at the primary & secondary schools in the parish will be supported”  *N.b.This Action Point has been changed due to numbers of developments in the village and the lack of any planned provision for education*. | Dialogue established with Wainhomes & Primary school governors for the field to go to the school. Feasibility study will include adjacent land offered by developer to help with expansion. Primary school to add a class to each year timeline to be ascertained.  Secondary school will be supported if it goes for expansion. Support for a visitor’s car park would be postive | **July 2024** |  |  |  |
| **Broughton**  **Neighbourhood Development Plan (BNDP)** | Plan accepted at referendum 18/10/2018 & adopted by Preston City Council (PCC) 13/12/2018  Any additional action points generated by VIS to be added to this PAP. | The Parish Council will review and refresh the Neighbourhood Development Plan> see Review  Central Lancashire Plan : call for sites 3 completed. Consultations completed report with recommendations awaited delayed.  As the CLP has been further delayed the BNDP review will continue with tis Parish Consultations and submission in to the Inspector no later than July 2024  Any changes to the CLP polices will be integrated when adopted. | **November 2024**  **July 2024** |  |  | **5K** |
| **Planning &**  **Development** | The Parish Council will make sure all new residential properties in the Village comply with the Neighbourhood Development Plan policies and draft design code.  The Community concerns about further  development in the Village will be integrated into this action plan and prioritise the PC’s  Actions’ on future development.  The PC has represent the views of the BNDP & the Community at any relevant planning meetings, appeals and enquiries. | The BNDP review to include allocating one new site and a design code  PAP updated  Planning department are responding to our queries & supporting the PC in their review of the BNDP  The PC to continue to make representations and attend appeals where required. | **July 2024**  **May 2024**  **Ongoing** |  |  |  |
| **Heritage Assets**  PAP 9A & B | The inclusion of the heritage assets identified under Policy HE1 above on the Local List drawn up Preston City and in the LCC list  Detailed architectural study of buildings and vernacular features within the area to better understand their value and contribution to the history of the area with signage to inform the Renovation of the Pinfold & installation of Village information boards linked by Village trails.  The preservation of the Broughton St John Baptist Church hamlet including the lime trees on Church Lane planted in 1935 and Fernyhalgh.  War memorial to be listed  War memorial safety | Booklet on cottage updated  Broughton history book to be produced  New trail leaflets for Fernyhalgh and for Whittingham Lane to be produced for the Heritage weekend in October    Tree Preservation orders  Biographies of WW2 names on memorial added to website on D day & wreath  Fernyhalgh & West side Garstang Rd listed  . | **Completed**  **Ongoing**  **October 24**  **Ongoing**  **June 2024**  **Completed**  **Completed** | **£200**  **£50** |  |  |
| **Tree**  **Preservation**  PAP 1 | Review the existing Tree Protection  Orders (TPO)and where appropriate put forward proposals for further orders | Trees identified, using the form devised results sent still no response form PCC CC to be advised  Watching brief on new developments to make sure  (1) only trees agreed on applications to be removed  (2) the landscape plans agreed are adhered to | **Ongoing** |  |  |  |
| Agree with PCC a plan for the  management and future replacement of  ancient street trees and maintenance of hedgerows | **Ongoing** |  |  |  |
| **Community Facility**  **PAP 5 Dual use**  **PAP 6** | A centrally located community facility for Broughton Village will be secured either through dual use of an existing facility  The PC will work with local organisations such as the Broughton Club, Broughton High School and the St John Primary school to secure the extend duel usage of the indoor and outdoor facilities | Parish Council passed management to BPCC continuing support agreed  PC maintaining ownership of TBC  PC is exploring a dedicated community multiuse hall as part of the protecting green spaces & allotment projec> see Broughton Masterplan  BHS & BPS: dialogue established schools | **completed**  **ongoing**  **Ongoing** |  |  | £20000  £3000  £200000 |
| **Village scene**  PAP 15 Village PRoW  PAP 2 Drainage  PAP 13 Signage & Street  Furniture | The Parish Council will ……. seek to address any deficiencies and make improvements including the provision of benches.  Pursue the improvements to the PROW network to provide good linkage around the parish.  Lobby LCC & PCC for action on problems with local public drainage infrastructure | New estates to be looked at once completed  Play area on Eastway to be available  Bins in need of replacement ordered from PC  “New” borders in Village currently not being maintained  Village borders by bus stop, school entrance and crossroads to pass to BPC  Lengthsman employed, PROW prioritised  .  Flood map completed, monitoring in place | **Ongoing**  **completed**  **completed**  **2024**  **Ongoing** |  |  | **10K** |
| **King Georges Field**  PAP3 King George Playing Fields  PAP2  Drainage | The Parish Council looking at a package of Improvements the King George V Playing fields.  Ensure the KGV field is adequately drained specially maintaining the drainage system | Football pitches back in use, PC contributing to  Grass-cutting. Changing rooms will be updated with PCC  Enlarged and landscaped car park, update and moved playground new “nature area” to link to future park  Enhanced public facilities: paths, bins and benches  New drainage -survey by PCC as part park pns | **Ongoing**  **December 2024** | 1500 |  | **600K** |
| **Traffic speed**  **Management,**  **Highway maintenance & Parking**  PAP14  **PAP 10 Public & Shared use of private parking facilities**  **PAP11 on street car parking**  **PAP 12 Park & Ride** | Pursue the introduction of a 7.5T Environmental Weight Limit for the B5269 Woodplumpton/Whittingham Lane to remove any  Unnecessary ‘through’ Goods Vehicle Traffic.  Monitor traffic speeds and conditions for the safe movement of all highway users through the non-signal- controlled Broughton crossroads and consider any necessary further traffic management measures.  To work towards increasing the number of off-street car parking spaces available to the public.  Pursue appropriate Parking regulations on the local road network, especially Garstang Rd & Woodplumpton Lane, both of which are adversely affected by parked vehicles, which compromises traffic safety, both vehicular and pedestrian.  Liaise with the LCC on general road & pavement maintenance.  Park & Ride site in CLSP | The Parish Council are working with Preston City Council and Lancashire County Council on these matters. The weight limit for the through route to remain.  20mph is not being enforced, SPIDs in place on Garstang Road data with LCC Further Spid’s on Whittingham Lane.  LALC to lobby on enforcement of 20mph.  Parking zones signs are not specific to review with LCC  Parking see KGV field: part g KGV field scheme  To work with the enforcement officers enforce and high school pupils to increase awareness by using speed recorders. Hand-held SPIDS for YP purchased.  Yellow lines requested for Northway agreed no date as yet.    Monitored and reported through app  No decision as to future usage reached awaiting the CLCS publication in 2023/4. | **Ongoing**  **Ongoing**  **ongoing**  **Ongoing**  **Ongoing**  **Ongoing**  **Ongoing**  **Ongoing** |  |  | **3K** |
| **Public Transport**  **PAP 10,11,12 & 14** | PC will identify difficulties and deficiencies in such provision particularly for the elderly and disabled and raise these with the Highway authority, stagecoach and Preston bus | Concerns raised that the school/college passes only work on PCC vehicles not stagecoach no response as yet | **Ongoing** |  |  |  |  |  |
| **Increase protected green spaces**  **Consult 2020** | To look at a scheme to set up Allotment/Community Gardens in the Village  The Parish Council will explore other possibilities within the village to increase protected green spaces and area for public recreation. | Broughton Masterplan: Discussion taking place with FIT, the developers (& owner’s solicitors) & PCC parks & planning.  Topographical survey and draft plans discussed. | **Ongoing** |  |  |  |
| **Climate Change**  **Emergency**  **Consult 2020** | To look at how the Parish Council can promote measures relating to Climate change | To include positive statements in the revised Plan and to work with PCC | **Ongoing** |  |  |  |

The adopted plan is currently under review. The timeline is to have this ready for mid-June with a view to it being with the examiner in the autumn and the referendum later this year…

The next PAP in July will reference the revised PAP’s in the revised plan.